## Dashboard
FAMOUS BRANDS LIMITED — DUE DILIGENCE TRACKER
Growth Equity ¦ Deal Size: R13.0bn ¦ South Africa / Pan-Africa ¦ Date: 17 Mar 2026
WORKSTREAM PROGRESS SUMMARY
Workstream | Sheet | Total Items | Not Started | In Progress | Complete | Red Flags | % Complete | P0 Outstanding | Status
Financial DD | Financial DD | 24 | 20 | 0 | 0 | 0 | 0% | 11 | ⬜ Not Started
Commercial DD | Commercial DD | 22 | 18 | 0 | 0 | 0 | 0% | 8 | ⬜ Not Started
Legal DD | Legal DD | 18 | 15 | 0 | 0 | 0 | 0% | 8 | ⬜ Not Started
Operational DD | Operational DD | 16 | 13 | 0 | 0 | 0 | 0% | 4 | ⬜ Not Started
HR & People DD | HR & People DD | 13 | 10 | 0 | 0 | 0 | 0% | 2 | ⬜ Not Started
IT & Technology DD | IT & Tech DD | 15 | 12 | 0 | 0 | 0 | 0% | 1 | ⬜ Not Started
ESG & Regulatory | ESG DD | 16 | 13 | 0 | 0 | 0 | 0% | 3 | ⬜ Not Started
Consumer / Franchise | Consumer DD | 19 | 15 | 0 | 0 | 0 | 0% | 5 | ⬜ Not Started
TOTAL |  | 143 | 116 | 0 | 0 | 0 | 0% | 42
KEY DEAL PARAMETERS
Target Company | Famous Brands Limited (JSE: FBR)
Sector | Consumer / QSR & Casual Dining Franchisor
Deal Type | Growth Equity (Minority Stake)
Deal Size | R13.0bn
Geography | South Africa (primary), Sub-Saharan Africa, Middle East
Key Concern | Customer / Franchisee Concentration; Brand Concentration
LOI Target | TBC
Close Target | TBC
Lead Advisor | TBC
DD Status | Initiated

## Financial DD
Famous Brands — Financial DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
QUALITY OF EARNINGS (QOE)
1 | QoE Report — Management Accounts | Obtain FY2022–FY2025 audited financials + management accounts. IFRS-compliant. Focus on recurring vs. non-recurring items. |  | P0 - Gating | Not Started
2 | Revenue Bridge — Organic vs. Inorganic | Decompose revenue growth by: new restaurant openings, same-store sales growth (SSSG), royalty rate changes, manufacturing volumes. |  | P0 - Gating | Not Started
3 | EBITDA Adjustments & Normalisation | Identify one-off costs (GBK write-down residuals, restructuring, COVID relief, IFRS 16 lease reclassifications), management add-backs. |  | P0 - Gating | Not Started
4 | IFRS 16 Lease Analysis | Quantify right-of-use assets and lease liabilities. Understand impact on reported EBITDA vs. EBITDAL. Key given franchise model. |  | P1 - High | Not Started
5 | Manufacturing Division P&L | Separate Logistical Services (manufacturing, distribution) P&L from franchise segment. Assess intercompany pricing / transfer pricing. |  | P0 - Gating | Not Started
6 | Royalty & Franchise Fee Revenue Quality | Validate royalty rate structures by brand. Identify fixed vs. % of turnover fees. Confirm royalty collection history and bad debts. |  | P0 - Gating | Not Started
7 | Supply Chain Revenue Concentration | Assess revenue concentration by brand and franchisee group within manufacturing segment. |  | P0 - Gating | Not Started
WORKING CAPITAL & CASH FLOW
8 | Normalised Working Capital Analysis | 12-month trailing working capital. Identify seasonal peaks (December trading). Peg for SPA locked-box / completion accounts. |  | P0 - Gating | Not Started
9 | Capex — Maintenance vs. Growth | Split capex between: company-owned restaurant refurbs, manufacturing plant, IT systems, and growth (new territories). |  | P1 - High | Not Started
10 | Free Cash Flow Conversion | FCF = EBITDA – capex – working capital movements – tax paid. Target >75% conversion vs. EBITDA. |  | P1 - High | Not Started
11 | Dividend History & Capital Allocation | Review JSE dividend announcements, special dividends, and share buyback history (FY2019–FY2025). |  | P2 - Medium | Not Started
DEBT, TAX & BALANCE SHEET
12 | Net Debt & Debt-Like Items | Full net debt schedule including: borrowings, IFRS 16 lease liabilities, deferred consideration, contingent liabilities. |  | P0 - Gating | Not Started
13 | Pension / Retirement Fund Obligations | South African pension fund actuarial surplus/deficit. Any defined benefit exposure. |  | P1 - High | Not Started
14 | Tax Compliance — SARS | Confirm SARS compliance: PAYE, VAT, income tax. Any outstanding assessments or disputes. Section 45 / group restructuring history. |  | P0 - Gating | Not Started
15 | Deferred Tax & Tax Losses | Identify any unused tax losses (carry-forward). Understand temporary differences from accelerated depreciation. |  | P1 - High | Not Started
16 | Currency Exposure — Sub-Saharan Africa | Quantify revenues and EBITDA in non-ZAR currencies (Namibia, Botswana, Zambia, Ghana, Nigeria, Middle East). |  | P1 - High | Not Started
17 | Audit History & Accounting Policies | Review last 3 audit reports (PwC / Deloitte). Any qualified opinions, emphasis of matter, or restatements. |  | P0 - Gating | Not Started
PRO FORMA & PROJECTIONS
18 | Management Case Financial Projections (FY2025–FY2029) | Obtain management's 5-year plan. Stress-test SSSG assumptions, new restaurant rollout plan, and margin targets. |  | P0 - Gating | Not Started
19 | Run-Rate & Synergy Adjustments | Identify any cost-out opportunities or synergies relevant to the equity story (efficiency, supply chain leverage, digital). |  | P2 - Medium | Not Started
20 | Sensitivity Analysis — ZAR/Consumer | Model downside scenarios: consumer spending contraction, load-shedding impact, rand depreciation. |  | P1 - High | Not Started

## Commercial DD
Famous Brands — Commercial DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
MARKET & INDUSTRY
1 | South African QSR Market Size & Growth | TAM for SA QSR and casual dining. Historical growth (2018–2025). Impact of load-shedding on foot traffic and delivery volumes. |  | P0 - Gating | Not Started
2 | Consumer Spending Outlook | SA consumer confidence, disposable income trends, unemployment (35%+). Impact on trading in key LSM segments. |  | P1 - High | Not Started
3 | Delivery & Digital Market Shift | Assessment of third-party delivery (Uber Eats, Mr D) as % of brand revenue. Competitive dynamics vs. pure-play digital players. |  | P1 - High | Not Started
4 | Pan-African & Middle East Growth Opportunity | TAM for SSA expansion. Current footprint: Ghana, Nigeria, Kenya, Mauritius, Namibia, Botswana, Middle East. Growth pipeline. |  | P1 - High | Not Started
COMPETITIVE POSITIONING
5 | Brand Portfolio Competitive Map | Map Wimpy, Steers, Debonairs, Mugg & Bean, Fishaways, Tashas against competitors: McDonald's, KFC, Nando's, Spur, RCL Foods. |  | P0 - Gating | Not Started
6 | Market Share by Brand & Segment | Estimated market share by: burger QSR, pizza, fish, chicken, casual dining. Source: Euromonitor / NPD / internal data. |  | P1 - High | Not Started
7 | Franchisee Satisfaction Survey | Obtain or commission franchisee NPS survey. Red flag: franchisee grievances, non-renewals, system exits. |  | P0 - Gating | Not Started
8 | Brand Health Tracking | Consumer brand awareness, consideration, preference metrics by brand. Key vs. Nando's and McDonald's. |  | P1 - High | Not Started
CUSTOMER & FRANCHISEE CONCENTRATION (KEY RISK)
9 | Top 20 Franchisee Concentration Analysis | PRIORITY: Identify top 20 franchisees by number of restaurants and revenue contribution. Concentration risk if top 3-5 represent >20% of system. |  | P0 - Gating | Not Started
10 | Multi-Unit Franchisee (MUF) Agreements | Review terms for multi-unit operators. Rights of first refusal, territory exclusivity, performance covenants. |  | P0 - Gating | Not Started
11 | Franchisee Financial Health | Request anonymised franchisee P&L data. Assess viability (4-wall EBITDA margins). Red flag: franchisee distress could accelerate exits. |  | P0 - Gating | Not Started
12 | Brand Concentration by Revenue | What % of total system sales does Steers + Wimpy + Debonairs represent? Risk if legacy brands decline vs. premium (Tashas). |  | P0 - Gating | Not Started
13 | Contract Renewal & Retention Rate | Franchisee renewal rate over last 5 years, by brand. Non-renewal reasons. |  | P1 - High | Not Started
14 | New Franchisee Pipeline | Number of signed franchise agreements not yet open. Geographic split. Pipeline coverage ratio. |  | P1 - High | Not Started
PRICING, SALES & PIPELINE
15 | Menu Price Inflation History | Annual menu price increases vs. CPI, vs. SARB food inflation. Elasticity analysis. |  | P1 - High | Not Started
16 | Same-Store Sales Growth (SSSG) by Brand | Monthly SSSG for last 36 months by brand. Red flag: sustained negative SSSG in legacy QSR brands. |  | P0 - Gating | Not Started
17 | Restaurant Development Pipeline | New restaurant pipeline: signed, under construction, planned (12M / 24M). Split: South Africa vs. international. |  | P1 - High | Not Started
18 | Go-to-Market & Advertising Fund | Review National Advertising Fund (NAF) contributions, spend allocation, and franchisee disputes. |  | P2 - Medium | Not Started

## Legal DD
Famous Brands — Legal DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
CORPORATE STRUCTURE
1 | Group Corporate Structure Chart | Full legal entity map: holding company (Famous Brands Ltd), SA operating subsidiaries, international JV/franchise structures. |  | P0 - Gating | Not Started
2 | JSE Listing & Shareholder Register | Major shareholders (>5%), concert parties, institutional holders. Confirm no change-of-control provisions triggered. |  | P0 - Gating | Not Started
3 | Subsidiaries & Joint Ventures | List all subsidiaries, JVs, and associates. Focus on international structures (Middle East JV, African master franchise holders). |  | P1 - High | Not Started
MATERIAL CONTRACTS
4 | Master Franchise Agreements — International | Review all international master franchise agreements. Terms: territory rights, royalty rates, development obligations, renewal options. |  | P0 - Gating | Not Started
5 | SA Franchise Disclosure Documents (FDD) | Compliance with SA Consumer Protection Act (CPA) franchise disclosure requirements. Last update date. |  | P0 - Gating | Not Started
6 | Manufacturing Supply Agreements | Key supply agreements between manufacturing division and franchisees. Transfer pricing, exclusivity, and price escalation clauses. |  | P0 - Gating | Not Started
7 | Key Supplier Agreements | Review top 10 supplier contracts (packaging, proteins, buns). Single-source risk, pricing mechanisms. |  | P1 - High | Not Started
8 | Lease Portfolio Review | Corporate-leased properties (manufacturing, support office). Remaining lease terms, break clauses, renewal options. |  | P1 - High | Not Started
9 | Technology & Licensing Agreements | POS system licenses, loyalty programme (Famous Rewards) IP, digital ordering platform agreements. |  | P2 - Medium | Not Started
IP, COMPLIANCE & LITIGATION
10 | Trademark Portfolio | All brand trademarks registered in SA and key international markets. Any disputed marks (esp. Wimpy in UK/EU contexts). |  | P0 - Gating | Not Started
11 | Litigation History | All pending or threatened litigation. Focus on: franchisee disputes, employment claims, product liability, competition law. |  | P1 - High | Not Started
12 | Competition Commission History | Any prior investigations, settlements, or behavioural remedies under SA Competition Act. Sector has history of scrutiny. |  | P0 - Gating | Not Started
13 | Consumer Protection Act (CPA) Compliance | Review franchise disclosure compliance, cooling-off periods, food safety regulations (R638 Foodstuffs Regulations). |  | P1 - High | Not Started
14 | Employment & Labour Law | CCMA disputes, unfair dismissal claims. Compliance with BCEA, LRA, EEA. |  | P1 - High | Not Started
15 | BBBEE Compliance | Current BBBEE scorecard level and certificate. Ownership, management control, skills dev, enterprise/supplier dev components. |  | P0 - Gating | Not Started

## Operational DD
Famous Brands — Operational DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
MANAGEMENT & ORGANISATION
1 | Executive Team Assessment | CEO (Darren Hele or successor), CFO, COO, Brand MDs. Tenure, succession, contractual protections. |  | P0 - Gating | Not Started
2 | Key Person Risk | Identify top 5–10 key employees. Review notice periods, restraint of trade, retention incentives. |  | P1 - High | Not Started
3 | Organisational Structure | Headcount by function: brand management, marketing, operations support, manufacturing, finance, IT. |  | P1 - High | Not Started
4 | Management Incentive Plan (MIP) | Review LTI/STI structures. JSE-listed equity-settled share plan terms. Alignment with growth equity investor. |  | P0 - Gating | Not Started
MANUFACTURING & SUPPLY CHAIN
5 | Manufacturing Plant Assessment | Review Midrand and other production facilities. Capacity utilisation, maintenance capex requirements, regulatory compliance. |  | P0 - Gating | Not Started
6 | Load-Shedding Resilience | Generator capacity at manufacturing plants. Impact of Eskom load-shedding on production schedules and uptime. |  | P1 - High | Not Started
7 | Distribution Network | Cold-chain and ambient distribution network. 3PL vs. owned fleet. Route-to-market efficiency. |  | P1 - High | Not Started
8 | Food Safety & Quality Systems | FSSC 22000 / HACCP certification status. Last audit results. Product recall history. |  | P0 - Gating | Not Started
9 | Supplier Concentration Risk | Single-source ingredient risk. Top 5 suppliers as % of COGS. Alternative sourcing options. |  | P1 - High | Not Started
OPERATIONS & FRANCHISEE SUPPORT
10 | Franchisee Operations Manual & Standards | Review mystery shopper scores, QSC audit results by brand over last 3 years. |  | P1 - High | Not Started
11 | Restaurant Technology (POS & Digital) | POS system coverage and age. Integration with third-party delivery, loyalty (Famous Rewards), and back-office reporting. |  | P2 - Medium | Not Started
12 | Training & Development Infrastructure | Famous Brands Academy: capacity, franchisee training compliance rates, online vs. in-person capability. |  | P2 - Medium | Not Started
13 | Insurance Coverage | Product liability, property, business interruption, D&O, cyber. Adequacy of cover. |  | P2 - Medium | Not Started

## HR & People DD
Famous Brands — HR & People DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
WORKFORCE OVERVIEW
1 | Headcount & FTE Analysis | Corporate headcount (Famous Brands Ltd employees, not franchisees). By department and geography. Trend FY2021–FY2025. |  | P1 - High | Not Started
2 | Employment Equity (EE) Report | EEA2 / EEA4 reports. Top management and senior management transformation targets vs. actual. |  | P0 - Gating | Not Started
3 | Remuneration Benchmarking | Executive and management pay vs. SA market (Payscale / Remchannel data). Incentive structures. |  | P1 - High | Not Started
RETENTION & CULTURE
4 | Staff Turnover Rate | Annual voluntary attrition by band. Red flag: >20% corporate attrition may indicate cultural issues. |  | P1 - High | Not Started
5 | Employee Engagement Survey | Most recent engagement/culture survey results. eNPS score. |  | P2 - Medium | Not Started
6 | Key Employee Retention Risk | Identify C-suite and brand MD departure risk. Any recent departures or announced exits. |  | P0 - Gating | Not Started
BENEFITS & OBLIGATIONS
7 | Provident Fund / Retirement Funding | Defined contribution provident fund details. Any defined benefit legacy obligations. |  | P1 - High | Not Started
8 | Medical Aid & Benefits | Group life, disability, medical aid arrangements. Cost per employee trends. |  | P2 - Medium | Not Started
9 | Union & Labour Agreements | Any union recognition agreements. Sector bargaining council membership (SACCAWU/HORECASA). Past strike history. |  | P1 - High | Not Started
10 | CCMA & Labour Court Claims | Outstanding or settled unfair dismissal / retrenchment claims. Exposure quantum. |  | P1 - High | Not Started

## IT & Tech DD
Famous Brands — IT & Tech DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
TECHNOLOGY STACK
1 | ERP & Financial Systems | Core ERP (SAP, Sage, Oracle?). Integration with manufacturing, franchise billing, and reporting. Age and upgrade risk. |  | P1 - High | Not Started
2 | POS Systems — Brand Coverage | POS provider(s) by brand (e.g., Lightspeed, Oracle MICROS, custom). Age, cloud vs. on-premise. Integration to loyalty. |  | P1 - High | Not Started
3 | Loyalty Platform — Famous Rewards | Member base size, active users, redemption rates, data analytics capability. White-label vs. proprietary. |  | P1 - High | Not Started
4 | Digital Ordering & Delivery Integration | Own app capability. API integrations with Uber Eats, Mr D, etc. Revenue from digital channels as % of total. |  | P1 - High | Not Started
5 | Manufacturing IT Systems | MES / WMS systems in manufacturing plants. Automation level. Maintenance scheduling systems. |  | P2 - Medium | Not Started
CYBERSECURITY & DATA
6 | Cybersecurity Posture Assessment | Penetration testing history, SOC monitoring, endpoint protection, incident response plan. |  | P1 - High | Not Started
7 | Data Privacy — POPIA Compliance | SA Protection of Personal Information Act (POPIA) compliance: data mapping, consent management, POPIA officer appointment. |  | P0 - Gating | Not Started
8 | GDPR Exposure | Any EU customer / franchisee data held? GDPR compliance if applicable to international operations. |  | P2 - Medium | Not Started
9 | Cyber Incident History | Any prior breaches, ransomware events, or data leaks. Customer notification history. |  | P1 - High | Not Started
10 | IT Disaster Recovery (DR) Plan | RTO / RPO targets, DR testing frequency, cloud backup strategy. |  | P2 - Medium | Not Started
TECH ROADMAP
11 | 3-Year IT Investment Plan | Planned spend on IT and digital transformation. POS rollout, ERP upgrade, loyalty platform investment. |  | P1 - High | Not Started
12 | AI / Data Analytics Capability | Use of data analytics in menu engineering, franchisee performance, supply forecasting. |  | P2 - Medium | Not Started

## ESG DD
Famous Brands — ESG DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
ENVIRONMENTAL
1 | Integrated Report / Sustainability Report | Review Famous Brands Integrated Annual Report (IAR). GRI / TCFD disclosures. |  | P1 - High | Not Started
2 | Carbon Footprint & Scope 1/2/3 Emissions | Manufacturing emissions. Fleet emissions. Franchisee Scope 3 emissions strategy. |  | P2 - Medium | Not Started
3 | Water Usage — Manufacturing | SA water scarcity risk. Water consumption data for Midrand manufacturing facility. |  | P1 - High | Not Started
4 | Packaging & Waste Reduction | Single-use plastics compliance with SA regulations. EPR (Extended Producer Responsibility) scheme membership. |  | P1 - High | Not Started
5 | Energy & Load-Shedding Mitigation | Solar PV or generator capex at manufacturing plants. Renewable energy procurement. |  | P2 - Medium | Not Started
SOCIAL & GOVERNANCE
6 | BBBEE Scorecard — Full Detail | Level 4+ BBBEE required for major retail/government procurement. Ownership element critical if black shareholders. |  | P0 - Gating | Not Started
7 | Social Impact — Enterprise Development | Franchisee development programmes for black-owned franchisees. 51%+ black-owned franchise targets. |  | P1 - High | Not Started
8 | Food Nutrition & Health Obligations | Compliance with SA R429 food labelling regulations. Calorie disclosure, allergen labelling. Menu transformation risk. |  | P1 - High | Not Started
9 | Corporate Governance (King IV) | JSE-listed: King IV compliance. Board composition, independent non-executives, audit committee independence. |  | P0 - Gating | Not Started
10 | Related Party Transactions | Any material RPTs: director-linked franchisee interests, family connections. JSE Related Party Transaction rules. |  | P1 - High | Not Started
REGULATORY
11 | JSE Listings Requirements Compliance | History of JSE censures, cautionary announcements, major/category 1 transaction compliance. |  | P0 - Gating | Not Started
12 | Competition Commission — Market Inquiry | Monitor SA Competition Commission's Grocery Retail Market Inquiry and any food sector follow-on investigations. |  | P1 - High | Not Started
13 | International Franchise Regulations | Regulatory requirements in key markets: Nigeria (FIRS), Ghana, Kenya (CA), UAE (franchise law). Compliance status. |  | P1 - High | Not Started

## Consumer DD
Famous Brands — Consumer DD
# | Due Diligence Item | Description / Request | Data Room Ref | Priority | Status | Owner | Due Date | Notes / Red Flag Detail
BRAND PORTFOLIO ANALYSIS
1 | Brand P&L by Brand | Revenue, royalties, EBITDA contribution per brand. Identify any structurally declining brands (Milky Lane, Panarottis?). |  | P0 - Gating | Not Started
2 | Premium vs. Value Brand Mix | Segment brand portfolio by consumer segment. LSM 5-7 (value: Steers/Wimpy) vs. LSM 8-10 (premium: Tashas/Mugg & Bean). |  | P1 - High | Not Started
3 | Brand Refresh / Remodelling Capex | Scheduled brand revamps (e.g., Wimpy remodel programme). Franchisee capex commitment and Famous Brands co-investment. |  | P1 - High | Not Started
4 | Brand Sunset / Exit Risk | Identify brands where franchise agreement non-renewals have accelerated. Any brands being phased out. |  | P1 - High | Not Started
FRANCHISE SYSTEM HEALTH
5 | Total Restaurant Count Trend | System restaurant count by brand over FY2019–FY2025. Net new openings vs. closures. COVID recovery trajectory. |  | P0 - Gating | Not Started
6 | Franchisee 4-Wall Economics | Average franchisee revenue and 4-wall EBITDA margin. Payback period on investment. Comparison vs. competing systems. |  | P0 - Gating | Not Started
7 | Franchisee Application Pipeline | Number of qualified applicants. Approval rate. Financial requirements. Geographic target areas. |  | P1 - High | Not Started
8 | Corporate vs. Franchised Restaurants | Number of company-owned restaurants (direct exposure). Strategy — are they converting to franchise or holding? |  | P1 - High | Not Started
9 | International Master Franchisee Performance | Restaurant count and SSSG in SSA (Nigeria, Ghana, Kenya, Mauritius). Middle East performance. |  | P1 - High | Not Started
CONSUMER & DIGITAL
10 | Famous Rewards Loyalty Programme | Active member count, annual transaction volume, digital engagement rate. Monetisation of data. |  | P1 - High | Not Started
11 | Digital Sales Mix | App orders + third-party delivery as % of system sales by brand. Trajectory 2021–2025. |  | P1 - High | Not Started
12 | Consumer NPS by Brand | Brand Net Promoter Score (NPS) trend. Key detractor themes. |  | P1 - High | Not Started
13 | Social Media & Brand Sentiment | Share of voice vs. KFC, McDonald's, Nando's. Crisis history (social media boycotts, food safety incidents). |  | P2 - Medium | Not Started
GBK POST-DISPOSAL LIABILITIES
14 | GBK Residual Liabilities | Confirm no residual exposure from 2020 GBK (Gourmet Burger Kitchen UK) disposal / CVA process. |  | P0 - Gating | Not Started
15 | UK Creditor / Lease Claims | Any continuing obligations under GBK property leases or creditor claims in the UK that may still be outstanding. |  | P0 - Gating | Not Started

## Red Flag Log
Famous Brands — Red Flag Log
# | Workstream | Red Flag Description | Date Identified | Severity | Mitigant / Path to Resolution | Valuation / Deal Impact | Owner | Status
1 | Financial DD | Validate if any GBK-related residual losses remain in P&L |  | Deal-Breaker |  | Potential restatement risk |  | Open
2 | Commercial DD | Customer / franchisee concentration — top 20 franchisees to be quantified |  | Significant |  | May require contractual protections / MFO agreements |  | Open
3 | Legal DD | Competition Commission prior dealings — confirm no remedies attached to current operations |  | Significant |  | Seek clean bill from competition counsel |  | Open
4 | ESG DD | BBBEE level — growth equity structure must not dilute ownership component |  | Significant |  | Restructure deal to preserve BBBEE compliance |  | Open